## Hoja1
RISK REGISTER
Risk ID | Description | Likelihood | Impact | Severity | Owner | Mitigation Actions | Status
R1 | Changing stakeholder requirements | High | High | Medium | Product Owner | Regular sprint reviews with stakeholders to gather feedback early; maintain a prioritized product backlog. | Open
R2 | Team member unavailability | Medium | High | High | Scrum Master | Cross-train team members; maintain documentation for knowledge transfer. | Open
R3 | Technical issues with integration | Medium | Medium | Low | Development Team | Perform thorough testing in each sprint; allocate time for debugging and integration tasks. | Open
R4 | Delays in approvals from stakeholders | Medium | High | High | Stakeholders | Set clear deadlines for feedback and approvals; maintain open communication channels. | Open
R5 | Insufficient testing | Low | High | Low | QA Team | Implement test-driven development (TDD); conduct unit, integration, and acceptance testing in each sprint. | Open
R6 | Miscommunication among team members | Medium | Medium | Low | Scrum Master | Use collaboration tools (e.g., Trello); hold daily standups to align team efforts. | Open
R7 | Non-compliance with legal protocols | Low | High | High | Legal Advisor | Conduct reviews with legal advisors and ensure compliance with laws and regulations in requirements. | Open